NORTH LANARKSHIRE COUNCIL

REGENERATION SERVICES DIVISION

MINUTES OF KV LEADER PROGRAMME

Held at Twechar Healthy Living Centre on 23/10/09

Present: 	Diane McGill		North Lanarkshire Council					Paul Kane 		North Lanarkshire Council

Gillian Wightman	North Lanarkshire Council

Ellen Archibald		North Lanarkshire Council

Mary Coulshed		East Dunbartonshire Council				Frances Tonner		East Dunbartonshire Council				Paul Carter		Croy Community Council/Kilsyth & Villages Forum	Ian Jarvis 		Friends of Kelvin Valley Park				Gillian Barrie		Central Scotland Forest Trust				Arthur Kellar		Scottish Natural Heritage

Lorna Ewan		Historic Scotland

Catherine Martin		Kilsyth Villages Forum

John Farrell		Forestry Commission

Lesley Williamson	NLC Childcare Partnership

Item No.	Subject	Action By

- Welcome and Introduction

Diane McGill welcomed everyone to the third round scoring

LAG meeting, and introduced the programme of events for the

afternoon.

- Round 3 Update

Promotion of Activities – There has been 2 funding surgeries, which were well advertised however no-one attended.  Separate phone calls were received from groups looking for individual appointments.

Report on Activities – Will be discussed later in the meeting, technical checks are completed.

- Previous Approved Project Performance

All projects have been visited on initial approved.  Circulated paper highlights claims to date and project performance.  Formal monitoring visit to be arranged for the project that hasn’t claimed.  Spending profiles can only be highlighted if claims are received.  Formal report to be brought back to the LAG by written procedure.	CT

- LEADER Programme Performance

The Scottish government has highlighted that a total of only £6000 has been spent through Kelvin Valley LEADER, and are concerned about underspends, spends have to be reported to the European Commission.

- LEADER Applications and Scoring

LEAD027 CSFT Silver Birch Community Garden

£35,000 grant requested 37% of Project Costs

Outcome : Approved

LEAD028 Explore Lennoxtown & The Campsies

£5020 grant requested 50% of Project Costs

Outcome: Approved

LEAD029 NLC Antonine Wall

£30,000 grant requested 50% of Project Costs

Outcome: Approved

LEAD031 NLC Burngreen

£45,000 grant requested 32.5% of Project Costs

Outcome: Approved

LEAD032 Cumbernauld College Artist In Residence

£12,294 grant requested 50% of Project Costs

Outcome: Approved subject to assurance of community artist, promotion of the Kelvin Valley and agreement of a project brief to the LAG.	JO/CT

LEAD033 FKVP Walkers are Welcome

£5,450 grant requested 50% of Project Costs

Outcome: Approved

LEAD034 Waterways Trust Sense and Sensitivities

£35059 grant requested 50% of Project Costs

Outcome: Rejected, if able to come back in a future round application should be more streamlined, LAG have concerns on outputs and level of funding.  No evidence of past expenditure.

LEAD035 KSI Luggie Park

£10,960 grant requested 50% of Project Costs

Outcome: Approved subject to clarification on focus, drainage, promotion and benefits.

- Scottish Natural Rural Network Event

Looking for potential dates and venues for SCVO event, LAG decided Colzium House and a date in May 2010.  Potential projects, Kirkintilloch Canal Festival, Kilsyth Festival and the Walkers are Welcome Conference.

- SRDP & LEADER Update

LEADER projects in future round could be funded at a 90% intervention rate in response to the current economic climate.

- AOCB

Further round towards the end of February, the LAG decided on a date of the 22nd of February for the next meeting venue to be confirmed.