NORTH LANARKSHIRE COUNCIL

REGENERATION SERVICES

Minutes of KV LEADER Local Action Group (LAG)

held in

East Dunbartonshire Campus of Cumbernauld College

Kirkintilloch Learning Centre 
Southbank Road
Kirkintilloch
Glasgow
G66 1NH 
on

27/04/11

Present: 	Mary Coulshed		East Dunbartonshire Council

Paul Kane 		North Lanarkshire Council

Frances Tonner		East Dunbartonshire Council				Paul Carter		Croy Community Council/Kilsyth & Villages Forum	Gillian Barrie		Central Scotland Forest Trust

Ian Jarvis 		Friends of Kelvin Valley Park

Arthur Keller		Scottish Natural Heritage

Craig Clelland		Twechar Youth Group

Ellen Archibald		North Lanarkshire Council

Apologies:	Catherine Martin		Kilsyth Villages Forum

Jim O’Donnell		Cumbernauld College

Lesley Murray		Cumbernauld Childcare Network

Angus Clarke		Forestry Commission

Tracy Peedie		British Waterways Trust

Item No.	Subject	Action By

- Welcome and Introduction

Mary Coulshed (MC) opened the meeting by thanking everyone in attendance.  She explained the previous agreement that she would adopt the position of Chair as a replacement for Diane McGill who had now left the employ of North Lanarkshire Council

2	Previous Minutes

MC asked the meeting to consider the previous minutes for accuracy and matters arising.  The minutes were taken as a true record of the meeting.

Matters Arising

Paul Kane (PK) advised that he had passed the LAG contact details to Kirsty Gray to enable LAG members.  Partners confirmed that they had fed into the process to inform the future of the Kelvin Valley Action Plan.

Ellen Archibald (EA) & Frances Toner (FT) confirmed that they had raised awareness of Round 6 of the LEADER Programme via various publications and the website.

3	Programme Update (Report)

PK tabled a report which provided the LAG with an update on:

(i)	The status of approved LEADER projects

- The programme’s current financial commitment and

expenditure

(iii)	Monitoring Arrangements; and

- Overall LEADER Programme Status

PK talked to the report highlighting the key points from the report:

- with the exception of one project which had advised of an

anticipated underspend of £14k that 2010 approved projects were well underway to final claims.

- the project, approved in January 2011 with an allocation from the Rural Priorities funding, had started and had an anticipated end date of September 2011.

He further advised that:

- the Scottish Government would implement a monitoring and project visit on 26 July 2011;

- the Rural Payments Inspection Directorate would implement an inspection in early August 2011 but had already selected Kelvin Valley Festival for a random project audit which the team complied with;

- The programme annual report is required to be submitted by 13 May 2011; and

- NLC’s Audit Team would implement an internal audit in September 2011.

- Decision on Project Submissions – Rural priorities Measures

321 & 341 (Report & Discussion)

PK tabled an outline of the 9 final bids received for consideration in LEADER Round 6,  Community Facilities & Resources, Reference No(s). LEAD041-049 which provided the following project information: lead body name; project description; total cost; LEADER grant request; the applicable intervention rate; and the average score and ranking from the LAG assessments.

It was noted that the total request from LEADER calculated at £333,665 with £201,000 (includes £14,000 under spend identified under Item 3) available for distribution.  However following a detailed discussion on a range of options available to enable the LAG to prioritise the bids.  However the consensus arrived at was a preference to focus on smaller community groups delivering services in local areas, otherwise each project should be taken on its own merits.

Further discussion demonstrated a need for the LAG  to set  clear limits in terms of the minimum and maximum amount of award that could be provided by the LAG despite the increase in the intervention rate to 90%.  Consequently it was agreed that the LAG would continue with the status quo in terms of maximum and minimum grant awards of Min 5k & Max £50k.

During discussions: Paul Carter (PC) declared his interest in LEAD041 & 049; Craig Clelland declared his interest in LEAD047; and both left the meeting at the relevant point of discussion.

The LAG considered the 9 bids based on the criteria outlined above and made the following decisions:

| Ref. No. | Project Organiser | Project Description | Total Request From LEADER | Decision |
| --- | --- | --- | --- | --- |
| LEAD041 | Banton CAG | Sports area | £59,807 | £50,000 |
| LEAD042 | Campsie Trust | Changes to hall | £17,479 | £17,479 |
| LEAD043 | Croy Miners | Changes to layout | £50,000 | £42,818.00 |
| LEAD044 | Holy Cross Parent Council | Croy Sports Facility Fit-out | £65,333 | Reject |
| LEAD045 | Old Library | Changes to Hall | £2,700 | Reject Not eligible |
| LEAD046 | Queenzieburn C.C. | Comm Centre Floor replaced | £22,482 | £22,482 |
| LEAD047 | Twechar CA | Solar PVs | £33,030 | £33,030 |
| LEAD048 | Waterways Trust | Canal Improvements | £41,400 | Reject – Low priority |
| LEAD049 | Banton Comm Centre | Hall Improvements | £41,434 | £34,957 |
|  | TOTAL |  | £333,665 | £200,766 |

The reasons for these decisions were:

LEAD041: Project approved but capped at project maximum grant of £50,000.  To be discussed with applicant re match funding.

LEAD042: Project approved unanimously by LAG members

LEAD043:  Some debate about the extent of the work required by the project. After further discussion and bearing in mind the level of grant available to projects the LAG agreed to award £42,818 of grant.  Further discussion required with project applicant.

LEAD044:  After some debate the project application was rejected on the grounds that it appeared to be part of a wider North Lanarkshire Council project and was of a scale that the fund could not support.

LEAD045:  Project did not meet minimum spend and was rejected.  However, LAG requested that the Co-ordination team assist the applicant to identify other sources of grant that were more appropriate to this project.

LEAD046: Project approved unanimously by LAG members.

LEAD047:  High scoring project which was approved unanimously by LAG members.

LEAD048: Rejected on the grounds that its eligibility under this measure was questionable and the project did not have the same immediate benefit for small community groups that others had.

LEAD049: Some debate about the extent of the work required by the project. After further discussion and bearing in mind the level of grant available to projects the LAG agreed to award £34,957 of grant.  Further discussion required with project applicant.

It was noted that available funds had required the LAG to reduce awards in some cases.  Consequently the LAG delegated authority to the Co-ordination Team to increase awards by a maximum of 10% if underspends were declared in the future with a particular focus on the bids that had received reduced awards.  Otherwise any requests for increases should be forwarded electronically to the LAG for due consideration.  However particular emphasis was place on the need for all approved to confirm match funding, commence within 3 months of award and complete by the end of 2011.

- LEADER Post 2013

PK provided a verbal update on the LEADER Programme post 2013.  He informed the meeting the Cap Reform process will inform the next LEADER Programme.  However the Scottish Government is keen to maximise spend in the current programme.

- LAG – Future Meetings

The concluding discussion focussed on future meetings of the LAG.  However the decision taken was that unless the need for a meeting was identified, the Co-ordination Team to provide quarterly electronic /hard copy updates of the programme to the LAG.  Otherwise consideration should now be focussed on organising an event to celebrate the success of the Kelvin Valley LEADER Programme by showcasing its success.

- AOCB

There was no other competent business.

- Date of Next Meeting

As per the decision at Item 6 the next meeting of the LAG should be an organised event to celebrate the success of the Kelvin Valley LEADER Programme by means of showcasing successful projects.